## Sheet1
Application | # | Module | Activity | Task | Planned Hrs | Planned Start Date | Planned End Date | Actual Hrs | Actual Start Date | Actual End Date | Resource | Status | Remarks
Feedback Management System | 1 | Participant feedback Report form | Analysis | Requirement Analysis | 2 | 2018-02-27 | 2018-02-27 | 2 | 2018-02-27 | 2018-02-27 | Jyoti Mane, Babitha Nadar, Kalaga Vardhani, Channa Laxmi Sudheshna, Bhagyashree Joshi, Chamundeswari Gaddam, Ooha Gorle | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2018-02-27 | 2018-02-27 | 3 | 2018-02-27 | 2018-02-27 | Jyoti Mane, Babitha Nadar, Kalaga Vardhani, Channa Laxmi Sudheshana, Bhagyashree Joshi, Chamundeswari Gaddam, Ooha Gorle | Completed
|  |  |  | Preparing QFB | 1 | 2018-02-27 | 2018-02-27 | 1 | 2018-02-27 | 2018-02-27 | Babitha Nadar | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 3 | 2018-02-27 | 2018-03-03 | 4 | 2018-02-27 | 2018-03-03 | Jyoti Mane, Babitha Nadar, Kalaga Vardhani, Channa Laxmi Sudheshna, Bhagyashree Joshi, Chamundeswari Gaddam, Ooha Gorle | Completed
|  |  | Design | Unit Test Plan Preparation | 2 | 2018-02-28 | 2018-02-28 | 2 | 2018-02-28 | 2018-02-28 | Kalaga Vardhani | Completed
|  |  |  | LLD Preparation | 2 | 2018-02-28 | 2018-02-28 | 2 | 2018-02-28 | 2018-02-28 | Bhagyashree Joshi | Completed
|  |  |  | UTP Review | 1 | 2018-02-28 | 2018-02-28 | 1 | 2018-02-28 | 2018-02-28 | Jyoti Mane,Babitha Nadar | Completed
|  |  |  | UTP Rework | 1 | 2018-02-28 | 2018-02-28 | 1 | 2018-02-28 | 2018-02-28 | Kalaga Vardhani | Completed
|  |  |  | LLD Review | 1.5 | 2018-02-28 | 2018-02-28 | 1.5 | 2018-02-28 | 2018-02-28 | Jyoti Mane, Channa Laxmi Sudheshna | Completed
|  |  |  | LLD Rework | 1 | 2018-02-28 | 2018-02-28 | 1 | 2018-02-28 | 2018-02-28 | Bhagyashree Joshi | Completed
|  |  | Build | Coding | 10 | 2018-02-28 | 2018-03-03 | 11 | 2018-02-28 | 2018-03-05 | Channa Laxmi Sudheshna, Jyoti Mane, Babitha Nadar | Completed
|  |  |  | Code Self Review | 2 | 2018-03-05 | 2018-03-05 | 1.5 | 2018-03-05 | 2018-03-05 | Channa Laxmi Sudheshna, Jyoti Mane, Babitha Nadar | Completed
|  |  |  | Self Testing | 2 | 2018-03-05 | 2018-03-05 | 2 | 2018-03-05 | 2018-03-05 | Channa Laxmi Sudheshna, Jyoti Mane, Babitha Nadar | Completed
|  |  |  | Rework | 2 | 2018-03-05 | 2018-03-05 | 2.5 | 2018-03-06 | 2018-03-06 | Channa Laxmi Sudheshna, Jyoti Mane, Babitha Nadar,Kalaga Vardhani | Completed
|  |  |  | Code Peer Review | 0.5 | 2018-03-06 | 2018-03-06 | 0.5 | 2018-03-06 | 2018-03-06 | Kalaga Vardhani,Ooha Gorle,Chamundeswari Gaddam | Completed
|  |  |  | Code Integration | 4 | 2018-03-06 | 2018-03-06 | 4 | 2018-03-06 | 2018-03-06 | Channa Laxmi Sudheshna, Jyoti Mane, Babitha Nadar | Completed
|  |  |  | Integration Testing | 3 | 2018-03-07 | 2018-03-07 | 3 | 2018-03-07 | 2018-03-07 | Channa Laxmi Sudheshna, Jyoti Mane, Babitha Nadar,Kalaga Vardhani | Completed
|  |  |  | Rework | 2.5 | 2018-03-08 | 2018-03-08 | 2.5 | 2018-03-08 | 2018-03-08 | Channa Laxmi Sudheshna, Jyoti Mane, Babitha Nadar,Kalaga Vardhani | Completed
|  |  |  | Total Planned Hrs : | 43.5 |  |  | 45.5